## Risk Action Plan
EaaS RISK ACTION PLAN
One plan per High / Critical risk — complete after Risk Register prioritisation
RISK D — Performance Risk — Hardware / Software Malfunction
IDENTIFIED RISK | Performance Risk — Hardware / Software Malfunction
PROBABLE IMPACT | Unplanned equipment downtime; SLA breach → Liquidated Damages; customer operational disruption; relationship damage
PLANNED ACTIONS | 1. Deploy IoT predictive maintenance system 2. Establish trusted service partner network with SLA 3. Define response/resolution time commitments in contract 4. Set up 24/7 monitoring and alert protocol
REQUIRED RESOURCES | IoT monitoring platform; maintenance partner contracts; legal review of SLA clauses; internal technician training
PARTIES RESPONSIBLE | Provider Operations Manager (owner); Maintenance Partner; Legal; Customer IT (for data access)
PROPOSED TIMELINE | Pre-contract: SLA design (M-2); Installation: IoT setup (M0); Operations: monitoring live (M0+)
REPORTING PROCESS | Monthly SLA performance dashboard; quarterly risk review; incident report within 24h of each unplanned outage
MONITORING PROCESS | Uptime % vs. SLA target; mean time to repair (MTTR); number of SLA breaches per quarter; IoT alert response time
PREPARED BY | [Name] | DATE | [Date]
REVIEWED BY | [Name] | DATE | [Date]
RISK G — Credit Risk — Customer Fails to Pay
IDENTIFIED RISK | Credit Risk — Customer Fails to Pay
PROBABLE IMPACT | Unrecovered capital investment; legal collection costs; potential write-off; financier exposure
PLANNED ACTIONS | 1. Conduct customer creditworthiness assessment pre-contract 2. Negotiate credit insurance or bank guarantee 3. Include 3-invoice termination clause 4. Explore trade of receivables with financier
REQUIRED RESOURCES | Credit rating report; insurance broker; legal counsel; financial institution for receivables transfer
PARTIES RESPONSIBLE | Provider CFO (owner); Legal; Credit Insurer; Financier
PROPOSED TIMELINE | Pre-contract: credit assessment + insurance (M-3 to M-1); Contract signing: guarantee in place (M0)
REPORTING PROCESS | Invoice aging report monthly; escalation to CFO at 30 DPO; legal trigger at 3rd missed invoice
MONITORING PROCESS | Days Payment Outstanding (DPO); invoice dispute rate; insurance coverage status; receivables balance
PREPARED BY | [Name] | DATE | [Date]
REVIEWED BY | [Name] | DATE | [Date]
RISK A — Inadequate Pricing — Revenue-Cost Model Breakdown
IDENTIFIED RISK | Inadequate Pricing — Revenue-Cost Model Breakdown
PROBABLE IMPACT | IRR collapses; contract becomes loss-making; provider unable to sustain operations for contract duration
PLANNED ACTIONS | 1. Run EaaS price modelling tool (financing + insurance + O&M + usage variation + HR + tariff + early termination) 2. Select equipment with known O&M track record 3. Design modular system architecture 4. Integrate automated IoT billing to eliminate HR cost
REQUIRED RESOURCES | Price modelling tool; equipment O&M data; actuary for insurance cost estimation; IoT billing platform
PARTIES RESPONSIBLE | Provider CFO + Pricing Lead (owner); Equipment OEM; Insurer; IoT platform vendor
PROPOSED TIMELINE | Pre-contract: pricing model validated (M-4); Contract design: tariff formula agreed (M-2); Annual: price review
REPORTING PROCESS | Quarterly P&L vs. model; annual re-modelling with actual O&M vs. forecast; variance alert at >10% deviation
MONITORING PROCESS | Actual O&M cost vs. model; IRR tracking; energy tariff index vs. indexation formula; HR cost per contract
PREPARED BY | [Name] | DATE | [Date]
REVIEWED BY | [Name] | DATE | [Date]