## Risk Register
EaaS RISK REGISTER
Equipment-as-a-Service ¦ Provider · Client · Financier Risk Assessment
REF ID | RISK | STAKEHOLDER | RISK TRIGGER | CATEGORY | PROBABILITY 1–3 | IMPACT 1–3 | PI SCORE | RISK LEVEL | EXPECTED RESULT IF NO ACTION
A | Inadequate Pricing | Provider | Higher O&M costs / inaccurate financial model / underestimated HR | Financial | 2 | 3 | 6 | HIGH | IRR collapses; contract becomes loss-making over contract term
B | Volume Risk | Provider | Customer reduces operational hours / process changes / downturn | Financial | 2 | 3 | 6 | HIGH | Revenue shortfall; fixed costs unrecoverable from reduced consumption
C | Counterparty Demand Risk | Provider | Consumption deviates from design assumptions / technology underperforms | Operational | 2 | 2 | 4 | MEDIUM | Service unit revenue gap; provider bears cost of underperformance
D | Performance Risk | Provider | Hardware/software malfunction / SLA response time breach / power event | Technical | 3 | 3 | 9 | CRITICAL | Equipment downtime; SLA penalties; customer relationship damage
E | Early Contract Termination | Provider | Premises ownership change / customer insolvency / dissatisfaction | Legal | 2 | 2 | 4 | MEDIUM | Stranded asset; unrecoverable deployment and installation costs
F | Energy Tariff Change | Provider | Utility price increase borne by provider; significant % of TCO | Financial | 2 | 2 | 4 | MEDIUM | Margin erosion; pricing model uncompetitive vs. revised cost base
G | Credit Risk | Provider | Customer fails to pay invoices after equipment deployment | Financial | 2 | 3 | 6 | HIGH | Investment unrecovered; legal cost of collection; potential write-off
H | Construction & Completion | Provider | Installation delays / site access issues / permitting problems | Operational | 1 | 2 | 2 | LOW | Delayed revenue start; cost overrun; contractual penalty exposure
a | Provider Existential Risk | Client | EaaS supplier insolvency — service continuity breaks | Financial | 1 | 3 | 3 | MEDIUM | Client loses service continuity; no maintenance or repair support
b | Performance Risk (SLA) | Client | System breakdown / slow repair / availability SLA breach | Operational | 2 | 2 | 4 | MEDIUM | Customer operational disruption; breach of productivity targets
c | Data Protection Risk | Client | Remote monitoring exposes sensitive factory/process data — GDPR | Legal | 1 | 2 | 2 | LOW | GDPR penalty; reputational damage; competitive intelligence exposure
d | Force Majeure | Client | Natural disaster / pandemic / force majeure event | Regulatory | 1 | 2 | 2 | LOW | Complete service interruption; no remedy without contract clause
F1 | Credit Risk (Financier) | Financier | Provider or customer default on repayment obligations | Financial | 2 | 3 | 6 | HIGH | Principal not repaid; portfolio loss; asset collateral value destroyed
F2 | Ownership/Natrekking | Financier | Equipment reclassified as immovable property — ownership transfers to building owner | Legal | 2 | 3 | 6 | HIGH | Loss of equipment ownership; unable to repossess collateral

## Risk Management Matrix
EaaS RISK MANAGEMENT MATRIX
REF/ID | RISK | PRE-MITIGATION SEVERITY | PRE-MITIGATION LIKELIHOOD | PRE-MITIGATION LEVEL | MITIGATIONS / REMEDIES | POST-MITIGATION SEVERITY | POST-MITIGATION LIKELIHOOD | POST-MITIGATION LEVEL | RISK OWNER
A | Inadequate Pricing | Intolerable | Probable | EXTREME | Price modelling tool; modular equipment; IoT billing; track-record equipment selection | Undesirable | Possible | HIGH | Provider
B | Volume Risk | Intolerable | Probable | EXTREME | Historical consumption data; minimum consumption fee; Capacity Charge; careful customer selection | Tolerable | Possible | MEDIUM | Provider
C | Counterparty Demand Risk | Undesirable | Possible | HIGH | Site visit & process assessment; contractual min. usage clause (NL Cl. 9.1); no-alternative clause | Tolerable | Improbable | MEDIUM | Provider
D | Performance Risk | Intolerable | Probable | EXTREME | Predictive/preventive maintenance; trusted partner network; SLA liquidated damages; liability limits | Undesirable | Improbable | MEDIUM | Provider
E | Early Termination | Undesirable | Possible | HIGH | Customer-supplier relationship building; termination fees; minimum notice period; chain clause | Tolerable | Improbable | MEDIUM | Provider/Client
F | Energy Tariff Change | Tolerable | Probable | HIGH | Tariff indexation clause; electricity factor adjustment formula (60% elec + 40% CPI) | Acceptable | Improbable | LOW | Provider
G | Credit Risk | Intolerable | Possible | EXTREME | Trade of receivables / leasing; credit insurance; bank guarantee; customer creditworthiness check | Tolerable | Improbable | MEDIUM | Provider/Financier
a | Provider Existential Risk | Intolerable | Improbable | HIGH | Insolvency termination right; step-in rights for client; continuity clause | Tolerable | Improbable | MEDIUM | Client
b | Performance Risk (SLA) | Undesirable | Possible | HIGH | SLA with uptime guarantee; withholding payment rights; liquidated damages; 3rd party step-in | Acceptable | Improbable | LOW | Client
c | Data Protection | Tolerable | Possible | MEDIUM | GDPR data processing agreement; scope limitation clause; confidentiality; cyber insurance | Acceptable | Improbable | LOW | Client
F1 | Financier Credit Risk | Intolerable | Possible | EXTREME | National guarantee schemes (PMV, SRIW, Credendo); CEvaluator tool; partner selection | Undesirable | Improbable | MEDIUM | Financier

## Risk Assessment Matrix
EaaS RISK ASSESSMENT MATRIX
Likelihood × Consequence scoring grid ¦ Score = Probability × Impact
| LOW | MEDIUM | HIGH | CRITICAL
| OK to proceed | Take mitigation efforts | Seek support | Place on hold
|  | LOW Consequence (Insignificant) | MID Consequence (Moderate) | HIGH Consequence (Major/Catastrophic)
| HIGH Likelihood | MEDIUM | HIGH | CRITICAL
| MID Likelihood | LOW | MEDIUM | HIGH
| LOW Likelihood | LOW | LOW | MEDIUM

## Risk Breakdown Structure
EaaS RISK BREAKDOWN STRUCTURE
EaaS PROJECT RISK
PROVIDER RISKS |  | CLIENT RISKS | FINANCIER RISKS | COUNTRY-SPECIFIC
A — Inadequate Pricing |  | a — Provider Existential | F1 — Credit Risk | BE — Loss of Ownership (Natrekking)
B — Volume Risk |  | b — Performance (SLA) | F2 — Ownership / Natrekking | NL — Heat Act / Natrekking
C — Counterparty Demand |  | c — Data Protection |  | ES — Market Awareness / No Standard Contracts
D — Performance Risk |  | d — Force Majeure
E — Early Termination
F — Energy Tariff Change
G — Credit Risk
H — Other Risks