## EaaS Assumptions Ranking
EaaS RISKIEST ASSUMPTIONS RANKING TOOL
Highest Total Risk score = investigate first ¦ Score = Possibility (1–5) × Impact (1–10)
ASSUMPTION | TYPE (Problem / Solution / Implementation) | POSSIBILITY (1=unlikely wrong → 5=likely wrong) | IMPACT (1=trivial → 10=catastrophic) | TOTAL RISK (P × I) | PRIORITY ACTION
O&M cost model is accurate for selected equipment type over contract term | Solution | 3 | 9 | 27 | VALIDATE: run price model with 3 O&M scenarios
Customers will accept pay-per-use pricing vs. traditional capex purchase | Problem | 3 | 8 | 24 | TEST: pilot or customer interviews before contract
Consumption volume will match design assumptions over full contract term | Problem | 3 | 8 | 24 | VALIDATE: access 24+ months historical consumption data
Financier will accept EaaS receivables structure / trade of receivables | Implementation | 3 | 7 | 21 | VALIDATE: pre-screen with financier before contract
Customer credit risk is manageable within acceptable parameters | Problem | 2 | 9 | 18 | MITIGATE: creditworthiness assessment + credit insurance
Energy tariff will remain stable or adequately protected by indexation clause | Solution | 3 | 6 | 18 | MITIGATE: include tariff indexation formula in contract
IoT metering captures all billable usage events accurately and reliably | Implementation | 2 | 8 | 16 | TEST: pilot metering on one unit before rollout
Equipment performance meets SLA uptime targets in real operating conditions | Implementation | 2 | 8 | 16 | VALIDATE: track record data + predictive maintenance plan
Contract adequately protects provider from early termination cost exposure | Solution | 2 | 8 | 16 | VALIDATE: legal review of termination fee clauses
Customer will not install a competing system during contract term | Problem | 2 | 7 | 14 | MITIGATE: include no-alternative-system clause (NL Cl.15)
Equipment will not be classified as immovable property (natrekking risk BE/NL) | Solution | 2 | 6 | 12 | MITIGATE: equipment labelling + superficies rights clause
Remote monitoring access will not trigger GDPR compliance issues | Implementation | 1 | 7 | 7 | MITIGATE: GDPR data processing agreement + scope limits
SCORING GUIDE
≥ 24 | INVESTIGATE FIRST — Critical assumption
15–23 | HIGH PRIORITY — Validate before scaling
< 15 | MONITOR — Lower priority assumption