## Cover
EaaS TENDERING PROCEDURE
Opportunity Evaluation & Risk Assessment Toolkit
@PRATOLUIS
► CONTRACT TYPE SELECTION | Position opportunity on the performance contracting spectrum
► PRE-TENDER PROCESS | 7-step BP001 pre-tender readiness framework
► OBC SLA DESIGN | Outcome objectives, KPIs, payment logic & remedies
► RISK ASSESSMENT | EaaS 3-phase risk register by stakeholder
► MITIGATION STRATEGIES | Mitigation tool selection and go/no-go decision
@PRATOLUIS

## 1. Contract Type
EaaS TENDERING PROCEDURE — CONTRACT TYPE SELECTION
Part 1: Position the opportunity on the performance contracting spectrum before designing your response
OPPORTUNITY DETAILS
Opportunity Name:
Client / Account:
Industry Sector:
Country / Region:
Estimated Contract Value:
Contract Duration (years):
CONTRACT TYPE SPECTRUM — Risk Distribution
Contract Type | Pricing Model | Risk Bearer | Incentive Logic | EaaS Fit? | Speed to Contract | Innovation Level | Financing Impact
Activity-based (Cost-plus) | Time & materials | Customer covers all | Consume more hours/materials | ✗ No | Fast | Low | Customer capex
Type B — CPIF | Base + performance bonus | Mostly customer | Some incentive for provider | ◐ Partial | Medium | Medium | Customer capex
Type A — Pay for Performance ★ | Price per outcome unit | Provider bears ops risk | Optimize to deliver outcomes efficiently | ✓ YES — EaaS | Slower (M&V needed) | High | Provider capex / off-BS customer
Type C — FPI | Fixed + gain/pain share | Mixed, leaning provider | Shared savings model | ◐ Partial | Medium | Medium-High | Shared
Type D — Fixed Price | Lump sum all-in | Provider covers all | Maximum provider skin in game | ◐ Possible | Medium | High | Provider capex
OBC vs COST-PLUS — 6 Attribute Comparison
Attribute | Cost-Plus | OBC / EaaS (Type A)
Risk allocation | Customer bears all operational risk | Provider bears performance & availability risk
Incentive logic | Provider incentivized to consume hours/materials | Provider incentivized to deliver outcomes efficiently
Speed | Fast to contract; slow to deliver results | Slower to contract (M&V design); faster value delivery
Innovation | Low — no incentive to innovate | High — provider self-funds efficiency improvements
Monitoring burden | Customer monitors input activities | Customer monitors output KPIs; provider monitors internally
Financing implications | Customer finances asset; capex on customer balance sheet | Provider finances asset; enables off-balance-sheet treatment for customer
RECOMMENDED CONTRACT TYPE FOR THIS OPPORTUNITY:
RATIONALE:

## 2. Pre-Tender Readiness
EaaS TENDERING PROCEDURE — PRE-TENDER READINESS SCORECARD (BP001)
Part 2: Assess readiness across all 7 pre-tender process steps before the RFP drops
Step | Activity / Deliverable | Owner (Role) | Deadline | Status | Blockers / Notes
1 | MARKET ANALYSIS
1.1 | Research markets/sectors with upcoming equipment needs |  |  | In Progress
1.2 | Analyze industry trends; identify EaaS opportunity signals |  |  | Pending
1.3 | Produce ranked market opportunity map |  |  | Pending
2 | CLIENT IDENTIFICATION
2.1 | Identify clients via networks, relationships, competitor analysis |  |  | Pending
2.2 | Preliminary discussions — understand needs & decision-making process |  |  | Pending
2.3 | Qualify accounts: budget, authority, openness to OBC |  |  | Pending
3 | COMPETITOR ANALYSIS
3.1 | Map competitors likely to bid; research their EaaS capability |  |  | Pending
3.2 | Define differentiation narrative (technology, service, financing) |  |  | Pending
4 | RISK ASSESSMENT
4.1 | Conduct EaaS 3-phase risk assessment (see Tab 4) |  |  | Pending
4.2 | Develop preliminary mitigation strategies |  |  | Pending
5 | ADMINISTRATIVE PREPARATION
5.1 | Prepare company registration, financials, insurance, references |  |  | Pending
5.2 | Check IFRS 16/ASC 842 compliance for balance sheet treatment |  |  | Pending
5.3 | Ensure compliance with all expected RFP requirements |  |  | Pending
6 | INTERNAL ALIGNMENT
6.1 | Coordinate sales, technical, service, legal, finance stakeholders |  |  | Pending
6.2 | Secure board-level sponsorship for EaaS bid commitment |  |  | Pending
6.3 | Produce internal go/no-go memo with stakeholder sign-offs |  |  | Pending
7 | FEEDBACK & LEARNING
7.1 | Review feedback from previous tenders (won and lost) |  |  | Pending
7.2 | Document lessons learned; update pricing and SLA assumptions |  |  | Pending
STATUS KEY: Complete = green ¦ In Progress = amber ¦ Pending = white ¦ Blocked = red

## 3. OBC SLA Design
EaaS TENDERING PROCEDURE — OBC SLA DESIGN
Part 3: Define outcome objectives, KPIs, payment logic, and remedies for contractual enforcement
Outcome Objective | KPI | Target | Verification Method | Payment Logic | Remedy if Missed
Asset availability | Uptime % | ≥98.5% monthly | Machine telemetry + maintenance log | Full fee at threshold; pro-rata deduction below threshold | Service credit; mandatory corrective action plan
Production capacity | Throughput (units/hour) | ≥120 units/hour | MES or production line counter | Bonus above target; deduction below target | Re-tuning at supplier cost; no additional charge to client
Process efficiency | Cycle time (sec/unit) | ≤30 sec/unit | PLC timestamps | Shared savings formula if sustained below target | Temporary fee holdback until cycle time restored
Quality | FPY / Defect rate | ≥99.2% FPY or ≤0.8% defects | QA system + sample audit | Final acceptance contingent on quality window being met | Rework and replacement obligations at provider cost
Service responsiveness | MTTR | ≤2 hrs remote; ≤8 hrs onsite | Ticketing system + incident timestamps | Portion of fee tied to response time compliance | Escalating service credits per hour of delay beyond threshold
Energy / operating cost | kWh/unit or cost/unit | Baseline minus agreed % improvement | Smart metering + production records | Shared savings formula if improvement exceeded | Baseline reset via contract change; corrective review
CUSTOM OUTCOME OBJECTIVE (add as needed)
SLA DESIGN PRINCIPLES
1. Baseline first — all targets must reference a measured baseline. Never set targets without existing performance data.
2. Measurement before contract — agree on the verification method before signing. Measurement disputes are the #1 source of EaaS contract failure.
3. Bonus/penalty symmetry — if the provider can earn a bonus for outperformance, they bear a proportional penalty for underperformance.
4. Force majeure carve-outs — exclude customer-caused downtime, planned shutdowns, and external supply disruptions from SLA calculations.
5. Remedy ladder — remedies escalate: service credit → corrective action plan → termination right for persistent failure.
6. Quarterly SLA review — build in scheduled reviews with the option to reset targets as operations mature.

## 4. Risk Register
EaaS TENDERING PROCEDURE — RISK REGISTER (3-Phase EaaS Framework)
Part 4: Score all EaaS risks by phase and stakeholder ¦ Likelihood: Low/Mid/High ¦ Consequence: Low/Mid/High
Risk | Phase | Stakeholder | Likelihood | Consequence | Priority | Mitigation Action | Owner
PROVIDER RISKS (Technology Provider / Solution Provider)
Tech performance risk (HW/SW underperformance vs. contracted specs) | 3 | Provider | Mid | Mid | 🟡 AMBER
Hardware/software malfunction — downtime = no revenue + penalties | 3 | Provider | Mid | Mid | 🟡 AMBER
Metering device malfunction — affects billing accuracy | 3 | Provider | Mid | Mid | 🟡 AMBER
Tech provider existential risk — manufacturer insolvency | 1,2,3 | Provider | Low | High | 🔴 RED | Warranty + parts escrow agreement; backup supplier
Construction and completion risk — cost overruns and delays | 2 | Provider | Low | High | 🔴 RED | Performance bond; fixed-price construction contracts
Supply chain / service team risk — parts replacement reliability | 2,3 | Provider | Mid | Mid | 🟡 AMBER
Procurement / tariff risk — bureaucratic delays or tariff changes | 2 | Provider | Low | High | 🔴 RED | Tariff risk clause in contract; procurement buffer
Unanticipated maintenance risk — demand higher than forecast | 3 | Provider | Low | Mid | 🟢 GREEN
Service continuity risk — power outages, business interruptions | 3 | Provider/Customer | Low | High | 🟡 AMBER | SLA carve-out for force majeure; business interruption insurance
Customer change risk — ownership change during contract term | 3 | Provider | Mid | Mid | 🟡 AMBER | Change of control clause in contract
Counterparty existential risk — customer payment default | 2,3 | Provider/Financier | Low | High | 🔴 RED | Credit check; payment guarantee or insurance; advance fees
Counterparty demand risk — usage below/above contracted level | 3 | Provider | Low | Mid | 🟢 GREEN | Floor volume in contract; demand collar
Volume / residual value risk — equipment returned early | 3 | Provider/Financier | Mid | Mid/High | 🟡 AMBER | Early termination fee; residual value insurance
Balance sheet risk — transition from product to service model | 2,3 | Provider | Low | Low | 🟢 GREEN | IFRS 16 advisory; staged transition
Policy/regulatory and accounting standards risk (IFRS/ASC 842) | 2,3 | Provider | Low | High | 🟡 AMBER | Legal monitoring; regulatory change clause
Force majeure — war, pandemic, natural disaster, government action | 2,3 | Provider | Low | High | 🔴 RED | Force majeure clause; business interruption insurance
CLIENT RISKS (EaaS Customer)
Tech provider existential risk — service delivery ceases if provider insolvent | 1,2,3 | Client | Low | High | 🔴 RED | Require performance bond + spare parts escrow
System breakdown — manufacturing disruption during repair | 3 | Client | Mid | High | 🔴 RED | SLA with defined MTTR obligations and service credits
Slow response to repair — MTTR exceeds contractual limits | 3 | Client | Low | High | 🟡 AMBER | Contractual MTTR + escalating penalties
Force majeure — external events disrupt service delivery | 2,3 | Client | Low | High | 🟡 AMBER | Force majeure clause defining exclusions

## 5. Go - No-Go Decision
EaaS TENDERING PROCEDURE — GO / NO-GO DECISION BRIEF
Part 5: Score 5 dimensions Red/Amber/Green ¦ Any Red = No-Go ¦ 3+ Ambers = Conditional Go ¦ All Green = Go
Dimension | Rating (R/A/G) | Evidence / Assessment | Action Required
1. Strategic fit |  | Does opportunity align with target verticals and Type A OBC model? | Confirm client appetite for pay-for-performance contracting
2. Risk profile |  | Are all Red risks mitigated? Unmitigated Red = No-Go | Complete risk register (Tab 4); assign owners to all Red risks
3. Capability match |  | Can internal service team meet MTTR obligations in the SLA? | Confirm service coverage geographic footprint and response time data
4. Financial viability |  | Are unit economics positive at minimum SLA performance threshold? | Run pricing model at floor utilization; confirm positive margin
5. Internal alignment |  | Is there board-level sponsorship? Cross-functional team committed? | Get written sign-off from finance, legal, and operations leads
FINAL DECISION
DECISION: □ GO □ CONDITIONAL GO □ NO-GO |  | CONDITIONS ATTACHED (if Conditional Go):
Approved by:
Role:
Date:
MITIGATION TOOLS SELECTED FOR THIS OPPORTUNITY
Tool | Category | Applies to Risk | Status
PF4EE Instrument (EIB) | Financial — EU guarantee | Counterparty existential, financing risk
National Guarantee System | Financial — government | Credit risk, affordable debt access
Equipment Breakdown Insurance (HSB) | Financial — insurance | Technology risk, hardware malfunction
SLA Agreement (embedded in contract) | Contractual | Service continuity, slow repair, system breakdown
Force Majeure Clause | Contractual | Force majeure events — all stakeholders
Change of Control Provision | Contractual | Customer change risk (Phase 3)
Performance Bond | Financial — bonding | Construction and completion risk (Phase 2)
LAUNCH RAP V1.3 | Operational framework | Structured risk quantification pre-bid
IEEFP Mitigation Strategies | Operational framework | Financier due diligence alignment
EaaS Assistance Provider (ASG / Invigos) | Advisory | Management and financial implementation advice